## Sheet1
Project Title | Project Sponsor | Draft Business Case Produced/expected | Full Business Case Expected to be Submitted | CBC Internal Programme Board | Board Date Schedule | Update as at 9 July 2021
NB: Target date for all Business Case completion - December 2021 to allow for assessment, Board consideration and submission to CLG by March 2022
Canal Restoration | Chesterfield Canal Trust | draft case (90% complete on strategic & economic cases, 60% complete on other cases) by November 2021 | 2021-12-01 | 2022-01-01 | February 2022 (will be subject to Heritage Lottery Match Funding (decision due March 2022 for Stage One) | We met the Trust on 7 June - Heritage Lottery is sought for match funding. A stage 1 application in November is required for a Summer 2023 start for the Heritage element. The Trust has appointed consultants to support the business case development. They have requested support from the Capacity Funding and will identify specifc asks by end July.
DRIIVe | CBC | RIBA Stage II business plan produced | Expected Sept 2021 | 2021-10-22 | 2021-11-12 | Consultants are working on the Business Case
Hartington Industrial Park | SUON Ltd | mid September 2021 | early October 2021 | 2021-10-22 | 2021-11-12 | Potential Fast Track Project and start January 2022
Construction Skills Hub | CBC | Est. August 2021 | Expected September 2021 | 2021-10-22 | 2021-11-12 | Nth Degree Consulting appointed to develop the Feasibility Study
Staveley Miners Welfare FC Skills Academy | SMFC | Yes Draft received 26/4 | Expected June 2021 | 2021-06-18 | Approval by WP due 13 July 2021 | Potential Fast Track Project. Business case for consideration
Staveley Rail Station @ Barrow Hill | DCC/SCR | SOBC for the whole line produced; a date for a draft case for the station will be set once DfT has made its decision on taking the project to the next stage’. | TBA advised to be by Dec 2021 | 2022-01-01 | Feb 2022. | Awaiting Department For Transport approval - due imminently for the Barrow Hill rail line proposals as part of the Restoring Your Railway scheme.
Wheels to Work | DCC | TBA | TBA | TBA | Dec 2021. | JS presenting to Board on 16 July - update will be provided
Staveley 21 (town centre) | CBC | TBA, Masterplan work commenced | Est. December 2021 | 2021-12-17 | Feb 2022. | BDP Appointed to produce the Town Centre Masterplan from which specific projects will emerge with consultation for the Green book business case
Staveley Waterside | DCC | Yes Draft Received 12/4 | Expected July 2021 | 2021-09-24 | Oct 2021. | Draft business Case reviewed by Internal Programme Board on 18 June 2021, comments passed to DCC for consideration
Staveley Hall Conference Centre | Staveley Town Council | Yes - Received and in initial discussion with ARUP, Historic England meeting 21/5 | June 2021 (going to STC in May) | 2021-09-24 | Oct 2021. | Draft Business Case been reviewed by Historic England, ARUP and CBC planning & conservation team. Draft Business case will be reviewed by Internal Programme Board on 23 July.
Barrow Hill Memorial Hall | Barrow Hill Community Trust | Draft End September 2021 | expected December 2021 | 2022-01-01 | Feb 2022. | A Volunteer run Community Trust, they have requested support from the Town Fund Capacity Funding and will identify specifc asks by end July.We met with ARUP and Social Value team plus with Heritage Lottery 11 June. Aiming to submit stage one in August for the Heritage Enterprise Grant (inc revenue consultation work).
SMW Football Club - Skills Academy (Phase II) | Staveley Miners Welfare Football Club | Draft September 2021 | expected December 2021 | 2022-01-01 | 2022-02-01 | Phase II of this project. Will build upon the car park works of Phase I.