## Project Tracker
Project Title | Project Sponsor | Draft Business Case Produced/expected | Full Business Case Expected to be Submitted | CBC Internal Programme Board | External Appraisal | Board Date Schedule | Planned Submission of Summary Document to CLG | Update as at 25 Oct 2021 | Update as at 1 Oct 2021 | Update as at 9 Sept 2021 | Update as at 13 August 2021 | Update as at 9 July 2021
NB: Target date for all Business Case completion - December 2021 to allow for assessment, Board consideration and submission to CLG by March 2022
Canal Restoration | Chesterfield Canal Trust | draft case (90% complete on strategic & economic cases, 60% complete on other cases) by 11 October 2021 | 2022-01-14 | 2022-01-25 | 26 Jan - 8 Feb 2022 | 2022-02-16 | 2022-03-24 | Draft Business Case submitted for IPB, 5% Advance payment request and supporting evidence submitted. On Track | Good progress with Business case and materials acuisition such as clay. Putting details on the procurement and tenders | Payment for Capacity Funding released. Busienss Case being developed. | We met CCT on 27 July to work through specific project issues, timescales and risk register. Agreed to support with Capacity Funding (£10K). Also supported the planned HLF visit (due 20/8/21) Interested in accessing the 5% TD funding. | We met the Trust on 7 June - Heritage Lottery is sought for match funding. A stage 1 application in November is required for a Summer 2023 start for the Heritage element. The Trust has appointed consultants to support the business case development. They have requested support from the Capacity Funding and will identify specifc asks by end July.
DRIIVe | CBC | RIBA Stage II business plan produced | Expected Sept 2021 | 2021-10-22 |  | 2021-11-12 | Aim W/c 29 November | 5% Advance payment request submitted | No further update. | Met 9 Sept, business case and options, cost benefit ratio worked through, budget reductions but assessment for a viable and deliverable project. Presentation to Board on 17 Sept | Business Case Findings and recommendations of the options appraisal (due to be complete by 6th September). Setting up a 121 for 9 sept and project shall present to Board on 17th Sept. | Consultants are working on the Business Case.
Hartington Industrial Park | SUON Ltd | mid September 2021 | early October 2021 | 2021-11-19 |  | 2021-12-22 | Aim w/c 15 November, but Before 14 Jan deadline to draw down TD Funding | 5% advance not required, aiming to submit BC 29 Oct. | Site meeting planned for 5 October, busienss case timescale being firmed up | Planning Site meeting w/c 13 Sept then to submit planning application. | Been in touch by email twice, no news on draft busienss case | Potential Fast Track Project and start January 2022
Construction Skills Hub | CBC | Est. August 2021 | Expected September 2021 | 2021-11-19 |  | 2021-12-22 | Aim w/c 24 January | Draft BC produced, CBC reviewing. 5% Advance payment not required | N/A | N/A | FS Report submitted to CBC Officers, on track | Nth Degree Consulting appointed to develop the Feasibility Study
Staveley Miners Welfare FC Skills Academy | SMFC | Yes Draft received 26/4 | Expected June 2021 | 2021-06-18 |  | Approval by WP due 13 July 2021 | This element already approved, but advised to hold and submit summary doument alongside skills academy phase - therefore this will be before 14 Jan deadline to draw down TD Funding | Media Release ready to go live and all particlars (lease, contract signed). | funding agreement almost finalised. Procurement commenced. | Final Planning Permission, expected w/e 10 Sept. | Still awaiting PP - project sponsor has been chasing. Lease is acceptable to CBC and SMWFC, proceeding. Need to arrange contract, but SMWFC can't proceed withouth PP. | Potential Fast Track Project. Business case for consideration
SMW Football Club - Skills Academy (Phase II) | Staveley Miners Welfare Football Club | Draft September 2021 | expected December 2021 | 2022-01-25 |  | 2022-02-16 | 2022-02-25 | 5% Advance payment request submitted | Preparing busienss case for Skills Academy, due to submit draft shortly | N/A | No update | Phase II of this project. Will build upon the car park works of Phase I.
Staveley Rail Station @ Barrow Hill | DCC/SCR | SOBC for the whole line produced; a date for a draft case for the station will be set once DfT has made its decision on taking the project to the next stage’. | TBA advised to be by Dec 2021 | 2022-01-25 |  | 2022-02-16 | 2022-03-24 | Preparations in place for Board presentation and preparataions of draft Busienss Case. Awaiting DfT decision on Rail Line. 5% Advance payment request submitted. | Dependent upon DfT. Awaiting decision, expected as part of CSR. Draft outline business case being developed, presentation to Board on 12 November. | N/A | TD Chairman has had communication with Lee Rowley to arrange a meeting of key stakeholders to praise profile | Awaiting Department For Transport approval - due imminently for the Barrow Hill rail line proposals as part of the Restoring Your Railway scheme.
Wheels to Work | DCC | 17/09/2021 (for Internal Prog Bd 24 Sept) | November (considered by Int Prog Board 19 Nov) | 2021-12-17 |  | 2021-12-22 | 23/12/2021 (If fast tracked must be by 14 Jan) | Meeting with consultants to prepare business case this week. 5% advance not required | N/A | N/A | Has potential to be fast tracked. Town Deal Team met with DCC and RAD 6 Aug to discuss the project in detail. Draft BC end Sept, Full BC end October potentially and could begin in 21/22 | JS presenting to Board on 16 July - update will be provided
Staveley 21 (town centre) | CBC | TBA, Masterplan work commenced | Est. December 2021 | 2021-12-17 |  | 2022-02-16 | 2022-03-24 | Much work has been carried out by CBC team in the preparation for the Public Consultation (8 Nov - 12 Dec). Letter delivered to town centre businesses. Report live on line (25/10) | Cabinet paper being prepared, presentation to 12 November Board with details of the public consultation | Presentation to Board on 17 Sept. Draft Masterplan being developed and public consultation to commence before Christmas | Regular meetings to develop the Masterplan inc 9 Aug, 20 Aug and session with Hsg Team 16 Aug. Progress reported to SLT | BDP Appointed to produce the Town Centre Masterplan from which specific projects will emerge with consultation for the Green book business case
Staveley Waterside | DCC | Yes Draft Received 12/4 | Expected July 2021 | 2021-09-24 |  | 2021-10-29 | 2021-11-15 | Final draft busienss case submitted 25/10. 5% Advance not required. | N/A | Due to staff illness, a slight delay, but a further iteration of the Business Case being prepared and a report going to DCC Committee | Emailed a couple of times - no update to report | Draft business Case reviewed by Internal Programme Board on 18 June 2021, comments passed to DCC for consideration
Staveley Hall Conference Centre | Staveley Town Council | Yes - Received and in initial discussion with ARUP, Historic England meeting 21/5 | June 2021 (going to STC in May) | 2021-09-24 |  | 2021-10-29 | 2021-11-15 | second draft business case submitted, requirement of 5% to make progress. 5% Advance payment request submitted. | Business Case reviewed by IPB, requires 5% advance funding to progress the elements of the project. | Payment for Capacity Funding released | Meetings following the July Int Prog Board with STC 6 Aug, and Capacity Funding to support busienss case development and capacity requested and agreed. Interested in accessing the 5% TD funding. | Draft Business Case been reviewed by Historic England, ARUP and CBC planning & conservation team. Draft Business case will be reviewed by Internal Programme Board on 23 July.
Barrow Hill Memorial Hall | Barrow Hill Community Trust | Draft End September 2021 | expected December 2021 | 2022-01-25 |  | 2022-02-16 | 2022-02-25 | No request for 5% received. Sponsor has struggling with appointment of a consultacy support. | Awaiting information regarding Capacity Funding. No further update | Capacity Funding Claim form sent to Project sponsor | TD Team met Project sponsor 28 July, to agree timeline, capacity funding requested for support to write the busienss case, template tender specs provided to procure the support. Interested in accessing the 5% TD funding. | A Volunteer run Community Trust, they have requested support from the Town Fund Capacity Funding and will identify specifc asks by end July.We met with ARUP and Social Value team plus with Heritage Lottery 11 June. Aiming to submit stage one in August for the Heritage Enterprise Grant (inc revenue consultation work).