## Project Tracker
Project Title | Project Sponsor | Draft Business Case Produced/expected | Full Business Case Expected to be Submitted | CBC Internal Programme Board | External Appraisal | Board Date Schedule | Planned Submission of Summary Document to CLG | Update 9 February 2022 | Update 7 January 2022 | Update 15 Dec 2021 | Update 10 Dec 2021 | Update 1 Dec 2021 | Update as at 5 Nov 2021 | Update as at 1 Oct 2021 | Update as at 9 Sept 2021 | Update as at 13 August 2021 | Update as at 9 July 2021
NB: Target date for all Business Case completion - December 2021 to allow for assessment, Board consideration and submission to CLG by March 2022
Canal Restoration | Chesterfield Canal Trust | draft case (90% complete on strategic & economic cases, 60% complete on other cases) by 11 October 2021 | 2022-01-14 | 2022-01-20 | Draft submitted to TL 1 Dec. Revised version to be sent to TL 20 Dec 2021 for further review and return by 18 Jan. Final report by 8 Feb for Board | 2022-03-18 | 2022-03-24 | Earth work costs are very high, revisions are being carried out by the Project Sponsor. TL aware of issues and continue to prepare their report. | No Change | Met sponsor and revised draft to be sent 20 Dec for TL to further review | BC in with TL, 5% activities progressing and S151 approved | Procurement support in place, 5% inforamtion robust and contract in preparation. Timeline remains for the full Business Case. | Draft Business Case submitted for IPB, 5% Advance payment request and supporting evidence submitted & Approved 29 Oct. On Track | Good progress with Business case and materials acuisition such as clay. Putting details on the procurement and tenders | Payment for Capacity Funding released. Busienss Case being developed. | We met CCT on 27 July to work through specific project issues, timescales and risk register. Agreed to support with Capacity Funding (£10K). Also supported the planned HLF visit (due 20/8/21) Interested in accessing the 5% TD funding. | We met the Trust on 7 June - Heritage Lottery is sought for match funding. A stage 1 application in November is required for a Summer 2023 start for the Heritage element. The Trust has appointed consultants to support the business case development. They have requested support from the Capacity Funding and will identify specifc asks by end July.
DRIIVe | CBC | RIBA Stage II business plan produced | Expected 28 Jan 2022 | 24th Feb 2022 | 17/02/2022 | 2022-03-18 | 2022-03-24 |  | No Change | Business Case being prepared. Revised timetable but still deliverable for March submission | Business Case developing & on track | 5% supporting information provided 1 Dec. Business Case in hand. | 5% Advance payment request submitted & approved 29 Oct | No further update. | Met 9 Sept, business case and options, cost benefit ratio worked through, budget reductions but assessment for a viable and deliverable project. Presentation to Board on 17 Sept | Business Case Findings and recommendations of the options appraisal (due to be complete by 6th September). Setting up a 121 for 9 sept and project shall present to Board on 17th Sept. | Consultants are working on the Business Case.
Hartington Industrial Park | SUON Ltd | Recommend latest submission be Friday 18 Feb (TBA) | (TBA) 07/01/2022 | 24 Feb?? 2022 | TBA | 2022-03-18 | 2022-03-24 | Issues with WP and Business Case has not been received as yet. | Issues with WP and Business Case has not been received as yet. | N/A | Spoke with SW, agreed to press for fast track as it affects programme delivery. WP must work on plans and deliver | May not now on Fast Track list. Meeting with WP this week. | 5% advance not required, aiming to submit BC 29 Oct. | Site meeting planned for 5 October, busienss case timescale being firmed up | Planning Site meeting w/c 13 Sept then to submit planning application. | Been in touch by email twice, no news on draft busienss case | Potential Fast Track Project and start January 2022
Construction Skills Hub | CBC | Est. August 2021 | Expected November 2021 | 2021-11-19 | 2021-12-01 | 2021-12-22 | Aim w/c 24 January | Approved by TD Board | Approved by TD Board | On track for 22 Dec Board | Awaiting comments from TL. On track | Full Business case reviewd by IPB and sent to TL. | Draft BC produced, CBC reviewing. 5% Advance payment not required | N/A | N/A | FS Report submitted to CBC Officers, on track | Nth Degree Consulting appointed to develop the Feasibility Study
Staveley Miners Welfare FC Car Park element | SMFC | Yes Draft received 26/4 | Expected June 2021 | 2021-06-18 | N/A | Approval by WP due 13 July 2021 | This element already approved, but advised to hold and submit summary doument alongside skills academy phase - therefore this will be before 14 Jan deadline to draw down TD Funding | Approved, contracted and first Claim paid | N/A | N/A | Works commenced on track | Media release to be sent out this week, all confirmed | Media Release ready to go live and all particlars (lease, contract signed). Some planning conidtion issues still to be resolved | funding agreement almost finalised. Procurement commenced. | Final Planning Permission, expected w/e 10 Sept. | Still awaiting PP - project sponsor has been chasing. Lease is acceptable to CBC and SMWFC, proceeding. Need to arrange contract, but SMWFC can't proceed withouth PP. | Potential Fast Track Project. Business case for consideration
SMW Football Club - Skills Academy (Phase II) | Staveley Miners Welfare Football Club | Draft December 2021 | expected 14 Jan 2022 | 2022-02-09 | 2022-02-09 | 2022-03-18 | 2022-03-24 | Business Case being prepared, Training provider identified, design and planning application being prepared. | Business Case to be submitted 14 Jan. Met Sponsor 6 Jan for update. Training provider being selected, productinve meeting with CBC Skills Manager in Dec | (planning submission end Jan), meeting trainig providers this week. start May - Aug 2022 completion (may have £25K saving from car park element for this project) | Met sponsor and 5% application being prepared, meet with CBC Skills Manager 13 Dec |  | 5% Advance payment request submitted & approved | Preparing busienss case for Skills Academy, due to submit draft shortly | N/A | No update | Phase II of this project. Will build upon the car park works of Phase I.
Staveley Rail Station @ Barrow Hill | DCC/SCR | SOBC for the whole line produced; a date for a draft case for the station will be set once DfT has made its decision on taking the project to the next stage’. | TBA delay with DfT decision, this now is anticipated in Feb 2022, MLUHC have advised an extension is possible | 2022-02-09 | N/A | 2022-03-18 | 2022-03-24 | SOBC produced. Plan to recommend an extension for this project due to DfT delays | No change | DfT decision remains the critical factor. Met with Project Sponsor 13th and 15th Dec. A plan in place to submit an SOBC to proceed and submit to DLUHC by 24 March | Chairman has written to Mel DLUHC to impress urgency of DfT decision. | No announcements through the IRP. Anticipate Feb 2022 | Preparations in place for Board presentation and preparataions of draft Busienss Case. Awaiting DfT decision on Rail Line. 5% Advance payment request submitted. Board agreed to await DfT decision before release of 5%. | Dependent upon DfT. Awaiting decision, expected as part of CSR. Draft outline business case being developed, presentation to Board on 12 November. | N/A | TD Chairman has had communication with Lee Rowley to arrange a meeting of key stakeholders to praise profile | Awaiting Department For Transport approval - due imminently for the Barrow Hill rail line proposals as part of the Restoring Your Railway scheme.
Wheels to Work | DCC | TBA | TBA | TBA | IPB to appraise | 2022-03-18 | 2022-03-24 | No updates on how this project is developing. Awaiting Business Case, IPB shall appraise the project | Met sponsor 7 Jan, Business case due for IPB consideration 25 Jan for Board consideration on 16 Feb | Met sponsor 15 Dec, consultants working on the BC, | No news on how this project is developing | No news on how this project is developing | Meeting with consultants to prepare business case this week. 5% advance not required | N/A | N/A | Has potential to be fast tracked. Town Deal Team met with DCC and RAD 6 Aug to discuss the project in detail. Draft BC end Sept, Full BC end October potentially and could begin in 21/22 | JS presenting to Board on 16 July - update will be provided
Staveley 21 (town centre) | CBC | TBA, Masterplan work commenced | Est. January 2022 | 2022-02-24 | 2022-02-25 | 2022-03-18 | 2022-03-24 | Presentation on progress at 16 Feb Board. Business Cases being prepared, to submit to IPB and then TL. | Met consultants regarding business grant scheme 7 Jan, business cases are being developed. On track | Consultation concluded, Deliverable elements of masterplan being developed into business cases. | Consultation to conclude 12 Dec. Generally positive feedback, some concerns form specific affected busineses, but team are working with them. Business Cases being developed alongside and 5% request submitted. | Mid way through Masterplan, 5% detail has been received. Work on Business cases is underway. | Much work has been carried out by CBC team in the preparation for the Public Consultation (8 Nov - 12 Dec). Letter delivered to town centre businesses. Report live on line (25/10) | Cabinet paper being prepared, presentation to 12 November Board with details of the public consultation | Presentation to Board on 17 Sept. Draft Masterplan being developed and public consultation to commence before Christmas | Regular meetings to develop the Masterplan inc 9 Aug, 20 Aug and session with Hsg Team 16 Aug. Progress reported to SLT | BDP Appointed to produce the Town Centre Masterplan from which specific projects will emerge with consultation for the Green book business case
Staveley Waterside | DCC | Yes Draft Received 12/4 | Expected July 2021 & final received 25/10 | 19 Nov 2021 & 24/09/2021 & 20 Jan 2022 for final | 01/12/2021 - comments being reviewed | 2022-02-16 | 2022-02-25 | To be considered by Board on 16 Feb. Received DCC Cabinet Approval on 13 Jan 2022 | TL reviewing the business case and project sponsor has supplied additinoal information. Aim to bring to TD Board on 16 Feb | Timeline agreed 15 Dec. meeting 17 Dec to reivew TL comments DCC cabinet meeting 13 Jan 2022 |  | Still more work required on the BC, meeting to discuss is in hand | Final draft busienss case submitted 25/10. 5% Advance not required. | N/A | Due to staff illness, a slight delay, but a further iteration of the Business Case being prepared and a report going to DCC Committee | Emailed a couple of times - no update to report | Draft business Case reviewed by Internal Programme Board on 18 June 2021, comments passed to DCC for consideration
Staveley Hall Conference Centre | Staveley Town Council | Yes - Received and in initial discussion with ARUP, Historic England meeting 21/5 | June 2021 (going to STC in May) Final and full Business Case still awaited by TD Team. | 24/09/2021, but more details required for full and final Business Case | Draft 1 Dec 2021 | 2022-03-18 | 2022-03-24 | Sponsor utlising the 5% funding to progress the Business Case and Planning Application. Project sponsor working on feedback to TL. | TL working on feedback to project sponsor. Pre-app Planning meeting has taken place. | Awaiting TL comments | BC draft version sent to TL for comment. 5% approved | Pre-planning meeting taken place, 5% detail being submitted this week. | second draft business case submitted, requirement of 5% to make progress. 5% Advance payment request submitted and approved | Business Case reviewed by IPB, requires 5% advance funding to progress the elements of the project. | Payment for Capacity Funding released | Meetings following the July Int Prog Board with STC 6 Aug, and Capacity Funding to support busienss case development and capacity requested and agreed. Interested in accessing the 5% TD funding. | Draft Business Case been reviewed by Historic England, ARUP and CBC planning & conservation team. Draft Business case will be reviewed by Internal Programme Board on 23 July.
Barrow Hill Memorial Hall | Barrow Hill Community Trust | 2021-12-15 | 2021-12-16 | 17 December 2021 to review 20/01/2022 | 2022-01-21 | 2022-03-18 | 2022-03-24 | Business Case swith TL and project sponsor responding to comments from TL. | Draft Business Case submitted and considered by IPB. In reasonsable shape and consultants are on board working up the BC. | 5% application submitted 15 Dec. | Consultant appointed to prepare Business Case, Capacity funding released @ 11 Nov. 5% request has not been made as yet. Anticipating draft BC 15 Dec. tba | Consultant appointed to prepare Business Case, Capacity funding released @ 11 Nov. 5% request has not been made as yet. | No request for 5% received. Sponsor has struggling with appointment of a consultacy support. Sponsor has now appointed a consultant to work on all 5 cases, HB & IF met sponsor on 4 Nov | Awaiting information regarding Capacity Funding. No further update | Capacity Funding Claim form sent to Project sponsor | TD Team met Project sponsor 28 July, to agree timeline, capacity funding requested for support to write the busienss case, template tender specs provided to procure the support. Interested in accessing the 5% TD funding. | A Volunteer run Community Trust, they have requested support from the Town Fund Capacity Funding and will identify specifc asks by end July.We met with ARUP and Social Value team plus with Heritage Lottery 11 June. Aiming to submit stage one in August for the Heritage Enterprise Grant (inc revenue consultation work).