## Project Gantt Chart
Project Title & | Aug 21 | Sept 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22 | Apr 22 | May 22 | Jun 22
NB: Target date for all Business Case completion - December 2021 to allow for assessment, Board consideration and submission to CLG by March 2022
Canal Restoration
Draft Business Case by 11 October 2021 (achieved)
5% Advance Payment requested: |  |  | *
Internal Programme Board 22 October 2021 (draft)
Full Business Case by 14 January 2022
Internal Programme Board 25 January 2022
External Appraisal 1 Dec, but revised BC 20 Dec 2021 Report to CBC by 9 Feb
Town Deal Board Decision 16 February 2022
Submission to CLG by 24 March 2022 | CBC
Project Commencing TBA
DRIIVe
Draft Business Case to RIBA Stage II produced
5% Advance Payment requested: |  |  | *
Full Business Case by 17 January 2022
Internal Programme Board 9 February 2022
External Appraisal by 10 February 2022
Town Deal Board Decision 18 March 2022
Submission to CLG by 24 March 2022
Potential CLG funding release June 2022
Planning Permission submit end March 2022
Contractor appointed Feb 2023
Project Commencing March 2023
Hartington Industrial Park | SUON Ltd
Draft Business Case Est. 29 October 2021
Internal Programme Board 17 December 2021
Planning Permission (est Dec 21) May not be required for TD element to proceed
Full Business Case TBA, no new date provided
External Appraisal by TBA No new date provided
Town Deal Board Decision 18 March 2022
Submission to DLUHC by 24 March 2022
Western Power & potentially Contractor appointed Jan 2022 TBA
Project Commencing January 2022 (TBA - no new date provided)
Project Title | Aug 21 | Sept 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22 | Apr 22 | May 22 | Jun 22
Construction Skills Hub
Draft Business Case Est. August 2021
Full Business Case by 8 November 2021
Internal Programme Board 19 November 2021
External Appraisal by 1 December 2021
Town Deal Board Decision 22 December 2021
Submission to CLG by 14 January 2022
Planning Permission
Project Commencing September 2022 | SMFC
Staveley Miners Welfare FC Skills Academy (Phase I) | Staveley Miners Welfare Football Club
Town Board Approval by WP due 13 July 2021
Planning Permission
Lease Agreement
Project Commenced
SMW Football Club - Skills Academy (Phase II) | DCC/SCR
Draft Business Case 14 January 2022
Planning Permission
Full Business Case expected 14 January 2022
Internal Programme Board (for full BC) 25 January 2022
Town Deal Board Decision 16 February 2022
Submission to CLG by 24 March 2022
Project Commencing May 2022
Staveley Rail Station @ Barrow Hill
Awaiting Department For Transport approval (expected 27/10)
NB - Potential Extention for Business Case Submission
Draft case for the station will be set once DfT has made its decision on taking the project to the next stage
Draft Business Case updates and DfT issues advised 13 Dec 2021 | DCC
Internal Programme Board 25 January 2022
SOBC External Appraisal by 4 March 2022
Town Deal Board Decision 18 March 2022
Submission to CLG by 24 March 2022
Project Commencing TBA - dependent upon DfT
Wheels to Work | CBC
Draft & Full Business Case 13 Jan 2022
Internal Programme Board 20 Jan 2022
Full Business Case by 9 February 2022
Town Deal Board Decision 16 February 2022
Project commencment tba.
Project Title | Aug 21 | Sept 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22 | Apr 22 | May 22 | Jun 22
Staveley 21 (town centre)
Masterplan work commenced, presentation to Board 17 Sept & 12 Nov
NB - Potential Extention for Business Case Submission
Draft Business Case end Jan 2022
Internal Programme Board 24 February 2022
Full Business Case February 2022
Planning Permission
External Appraisal 25 Feb - 4 March 2022
Town Deal Board Decision 18 March 2022
Submission to CLG by 24 March 2022
Project Commencing TBA
Staveley Waterside | DCC
Draft Business Case Received 12 April 2021
Internal Programme Board on 18 June 2021
Full Business Case due Sept 2021 (delay due to staff illness) Rec'd 2nd draft 25 Oct 2021
Internal Programme Board on 19 Nov 2021 & 20 Jan 2022
Planning Permission TBA
External Appraisal by 22 November 2021 sent 1 Dec (comments being reviewed)
Town Deal Board Decision 16 Feb 2022
Submission to CLG by 24 March 2022
Project Commencing TBA PS to advise
Project Title | Aug 21 | Sept 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22 | Apr 22 | May 22 | Jun 22
Staveley Hall Conference Centre | Staveley Town Council
Draft Business Case been reviewed by Historic England, ARUP and CBC planning & conservation team 21 May 2021
Draft Business case Received June 2021
Internal Programme Board on 23 July
Staveley Town Council Meeting for approval 3 August 2021
Request for Capacity Funding made 6 August
2nd draft Business Case due 22 Sept 2021
Planning Permission
External Appraisal by draft sent 1 December 2021
Town Deal Board Decision 16 February/18 March 2022
Submission to CLG by 24 March 2022
Project Commencing June 2022 - Sept 2023
Project Title | Aug 21 | Sept 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22 | Apr 22 | May 22 | Jun 22
Barrow Hill Memorial Hall
Pre App meetings with Heritage Lottery June 2021
Presented to Board 14 May 2021
Request for Capacity Funding made 28 July
Draft Business case due Sept 2021 (not received)
Internal Programme Board 22 October 2021 (revised timescale tba)
Full Business Case due 15 December 2021
Planning Permission
External Appraisal by 13 December 2021
Town Deal Board Decision 16 February 2022
Submission to CLG by 24 March 2022
Heritage Lottery Match Funding decision due March 2022 for Stage One
Project Commencing TBA
Potential Fast Track Project - Start Dec 2021