## Project Tracker
Project Title | Project Sponsor | Draft Business Case Produced/expected | Full Business Case Expected to be Submitted | CBC Internal Programme Board | Board Date Schedule | Planned Submission of Summary Document to CLG | Update as at 9 Sept 2021 | Update as at 13 August 2021 | Update as at 9 July 2021
NB: Target date for all Business Case completion - December 2021 to allow for assessment, Board consideration and submission to CLG by March 2022
Canal Restoration | Chesterfield Canal Trust | draft case (90% complete on strategic & economic cases, 60% complete on other cases) by 29 September 2021 | 2021-12-09 | 2021-12-17 | Potentially 22 December 2021 (subject to Heritage Lottery Match Funding (decision due March 2022 for Stage One) | 2022-03-24 | Payment for Capacity Funding released. Busienss Case being developed. | We met CCT on 27 July to work through specific project issues, timescales and risk register. Agreed to support with Capacity Funding (£10K). Also supported the planned HLF visit (due 20/8/21) Interested in accessing the 5% TD funding. | We met the Trust on 7 June - Heritage Lottery is sought for match funding. A stage 1 application in November is required for a Summer 2023 start for the Heritage element. The Trust has appointed consultants to support the business case development. They have requested support from the Capacity Funding and will identify specifc asks by end July.
DRIIVe | CBC | RIBA Stage II business plan produced | Expected Sept 2021 | 2021-10-22 | 2021-11-12 | Aim W/c 29 November | Met 9 Sept, business case and options, cost benefit ratio worked through, budget reductions but assessment for a viable and deliverable project. Presentation to Board on 17 Sept | Business Case Findings and recommendations of the options appraisal (due to be complete by 6th September). Setting up a 121 for 9 sept and project shall present to Board on 17th Sept. | Consultants are working on the Business Case.
Hartington Industrial Park | SUON Ltd | mid September 2021 | early October 2021 | 2021-10-22 | 2021-10-29 | Aim w/c 15 November, but Before 14 Jan deadline to draw down TD Funding | Planning Site meeting w/c 13 Sept then to submit planning application. | Been in touch by email twice, no news on draft busienss case | Potential Fast Track Project and start January 2022
Construction Skills Hub | CBC | Est. August 2021 | Expected September 2021 | 2021-10-22 | 2021-11-12 | Aim w/c 29 November | N/A | FS Report submitted to CBC Officers, on track | Nth Degree Consulting appointed to develop the Feasibility Study
Staveley Miners Welfare FC Skills Academy | SMFC | Yes Draft received 26/4 | Expected June 2021 | 2021-06-18 | Approval by WP due 13 July 2021 | This element already approved, but advised to hold and submit summary doument alongside skills academy phase - therefore this will be before 14 Jan deadline to draw down TD Funding | Final Planning Permission, expected w/e 10 Sept. | Still awaiting PP - project sponsor has been chasing. Lease is acceptable to CBC and SMWFC, proceeding. Need to arrange contract, but SMWFC can't proceed withouth PP. | Potential Fast Track Project. Business case for consideration
SMW Football Club - Skills Academy (Phase II) | Staveley Miners Welfare Football Club | Draft September 2021 | expected December 2021 | 2022-01-25 | 2022-02-16 | 2022-02-25 | N/A | No update | Phase II of this project. Will build upon the car park works of Phase I.
Staveley Rail Station @ Barrow Hill | DCC/SCR | SOBC for the whole line produced; a date for a draft case for the station will be set once DfT has made its decision on taking the project to the next stage’. | TBA advised to be by Dec 2021 | 2022-01-25 | 2022-02-16 | 2022-03-24 | N/A | TD Chairman has had communication with Lee Rowley to arrange a meeting of key stakeholders to praise profile | Awaiting Department For Transport approval - due imminently for the Barrow Hill rail line proposals as part of the Restoring Your Railway scheme.
Wheels to Work | DCC | 17/09/2021 (for Internal Prog Bd 24 Sept) | November (considered by Int Prog Board 19 Nov) | 2021-12-17 | 2021-12-22 | 23/12/2021 (If fast tracked must be by 14 Jan) | N/A | Has potential to be fast tracked. Town Deal Team met with DCC and RAD 6 Aug to discuss the project in detail. Draft BC end Sept, Full BC end October potentially and could begin in 21/22 | JS presenting to Board on 16 July - update will be provided
Staveley 21 (town centre) | CBC | TBA, Masterplan work commenced | Est. December 2021 | 2021-12-17 | 2022-02-16 | 2022-03-24 | Presentation to Board on 17 Sept. Draft Masterplan being developed and public consultation to commence before Christmas | Regular meetings to develop the Masterplan inc 9 Aug, 20 Aug and session with Hsg Team 16 Aug. Progress reported to SLT | BDP Appointed to produce the Town Centre Masterplan from which specific projects will emerge with consultation for the Green book business case
Staveley Waterside | DCC | Yes Draft Received 12/4 | Expected July 2021 | 2021-09-24 | 2021-10-29 | 2021-11-15 | Due to staff illness, a slight delay, but a further iteration of the Business Case being prepared and a report going to DCC Committee | Emailed a couple of times - no update to report | Draft business Case reviewed by Internal Programme Board on 18 June 2021, comments passed to DCC for consideration
Staveley Hall Conference Centre | Staveley Town Council | Yes - Received and in initial discussion with ARUP, Historic England meeting 21/5 | June 2021 (going to STC in May) | 2021-09-24 | 2021-10-29 | 2021-11-15 | Payment for Capacity Funding released | Meetings following the July Int Prog Board with STC 6 Aug, and Capacity Funding to support busienss case development and capacity requested and agreed. Interested in accessing the 5% TD funding. | Draft Business Case been reviewed by Historic England, ARUP and CBC planning & conservation team. Draft Business case will be reviewed by Internal Programme Board on 23 July.
Barrow Hill Memorial Hall | Barrow Hill Community Trust | Draft End September 2021 | expected December 2021 | 2022-01-25 | 2022-02-16 | 2022-02-25 | Capacity Funding Claim form sent to Project sponsor | TD Team met Project sponsor 28 July, to agree timeline, capacity funding requested for support to write the busienss case, template tender specs provided to procure the support. Interested in accessing the 5% TD funding. | A Volunteer run Community Trust, they have requested support from the Town Fund Capacity Funding and will identify specifc asks by end July.We met with ARUP and Social Value team plus with Heritage Lottery 11 June. Aiming to submit stage one in August for the Heritage Enterprise Grant (inc revenue consultation work).

## Project Gantt Chart
Project Title & | Aug 21 | Sept 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22
NB: Target date for all Business Case completion - December 2021 to allow for assessment, Board consideration and submission to CLG by March 2022
Canal Restoration
Draft Business Case by 29 Sept 2021
Internal Programme Board 22 October 2021
Full Business Case by 9 December 2021
External Appraisal by 7 February 2022
Town Deal Board Decision 16 February 2022
Heritage Lottery Match Funding decision due March 2022 for Stage One (HLF Meeting on site 20 Aug)
Submission to CLG by 24 March 2022
DRIIVe
Draft Business Case to RIBA Stage II produced
Full Business Case by mid September 2021
Internal Programme Board 22 October 2021
Planning Permission
External Appraisal by 7 February 2022
Town Deal Board Decision 16 February 2022
Submission to CLG by 24 March 2022
Hartington Industrial Park
Draft Business Case Est. August 2021
Internal Programme Board 24 September 2021
Planning Permission
Full Business Case by mid September 2021
External Appraisal by 1 November 2021
Town Deal Board Decision 12 November 2021
Submission to CLG w/c 15 November 2021
Project Commencing January 2022
Project Title | Aug 21 | Sept 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22
Construction Skills Hub
Draft Business Case Est. August 2021
Full Business Case by mid September 2021
Internal Programme Board 22 October 2021
External Appraisal by 1 November 2021
Town Deal Board Decision 12 November 2021
Submission to CLG by 24 March 2022
Planning Permission
Project Commencing September 2022
Staveley Miners Welfare FC Skills Academy (Phase I)
Town Board Approval by WP due 13 July 2021
Planning Permission
Lease Agreement
Project Commenced
SMW Football Club - Skills Academy (Phase II)
Draft Business Case September 2021
Internal Programme Board 24 September 2022
Full Business Case expected December 2021
Internal Programme Board (for full BC) January 2022
Town Deal Board Decision 14 February 2022
Submission to CLG by 24 March 2022
Staveley Rail Station @ Barrow Hill
Awaiting Department For Transport approval
Draft case for the station will be set once DfT has made its decision on taking the project to the next stage
Draft Business Case advised to be by Dec 2021
Internal Programme Board January 2022
External Appraisal by 4 March 2022
Town Deal Board Decision 18 March 2022
Submission to CLG by 24 March 2022
Project Title | Aug 21 | Sept 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22
Wheels to Work
Draft Business Case 17 September 2021
Internal Programme Board 24 September 2021
Full Business Case by 18 October 2021
Town Deal Board Decision 29 October or 12 November 2021
Project could commence January 2022?? JS to advise
Staveley 21 (town centre)
Masterplan work commenced, presentation to Board 17 Sept
Draft Business Case 29 November 2021
Internal Programme Board 17 December 2021
Full Business Case February 2022
Planning Permission
External Appraisal by 4 March 2022
Town Deal Board Decision 18 March 2022
Submission to CLG by 24 March 2022
Staveley Waterside
Draft Business Case Received 12 April 2021
Internal Programme Board on 18 June 2021
Full Business Case due Sept 2021 (delay due to staff illness)
Internal Programme Board on 24 Sept 2021
Planning Permission
External Appraisal by 18 October 2021
Town Deal Board Decision 29 October 2021
Submission to CLG by 24 March 2022
Project Title | Aug 21 | Sept 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22
Staveley Hall Conference Centre
Draft Business Case been reviewed by Historic England, ARUP and CBC planning & conservation team 21 May 2021
Draft Business case Received June 2021
Internal Programme Board on 23 July
Staveley Town Council Meeting for approval 3 August 2021
Request for Capacity Funding made 6 August
Full Business Case due 15 October 2021
Planning Permission
External Appraisal by 1 November 2021
Town Deal Board Decision 12 November 2021
Submission to CLG by 24 March 2022
Barrow Hill Memorial Hall
Pre App meetings with Heritage Lottery June 2021
Presented to Board 14 May 2021
Request for Capacity Funding made 28 July
Draft Business case due Sept 2021
Internal Programme Board 22 October 2021
Full Business Case due November 2021
Planning Permission
External Appraisal by 13 December 2021
Town Deal Board Decision 14 January 2022
Submission to CLG by 24 March 2022
Heritage Lottery Match Funding decision due March 2022 for Stage One
Potential Fast Track Project - Start January 2022
Potential Fast Track Project - Start Sept 2021